## 1. Technical Impl. Plan
Appendix 4a
Project Implementation Plan: Technical Works
TYPICAL PUBLIC SANITATION FACILITY AND ON-SITE TREATMENT |  |  | Months | Month 1 |  |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  |  | Month 4
No | Description |  | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | Preparation of construction
| 1 | Issuing updated project time plan to contractor, WSB and WSTF | bar: Month 1 1
| 2 | Handing over site to contractor that is free of encumbrances | bar: Month 1 1
Training of contractor on special technical requirements and procedures | bar: Month 1 1
| 3 | Sensitization measures like installation of bill board to inform community | bar: Month 1 1
2 | Mobilisation of Contractor to Site
| 1 | Provide security at the construction sites | bar: Month 1 1 to Month 1 2
| 2 | Avail all equipment, tools and labour as appropriate to site | bar: Month 1 1 to Month 1 2
| 3 | Erect temporary site office where necessary | bar: Month 1 1 to Month 1 2
| 4 | Clearing site of bushes, grass and remove all roots | bar: Month 1 1 to Month 1 2
Inspection: Setting out the structure of toilet, on-site treatment, piping | bar: Month 1 2
3 | Toilet facility construction
3.1 | Toilet facility
| 1 | Excavation works | bar: Month 1 2
Inspection after finalization of excavation to verify proper levels | bar: Month 1 3
| 2 | Casting of foundation concrete | bar: Month 1 3
| 3 | Construction of the foundation wall | bar: Month 1 3 to Month 1 4
| 4 | Foundation backfilling and hardcore placing and compaction | bar: Month 1 4 to Month 1 5
| 5 | Hardcore blinding and casting of the floor slab | bar: Month 1 5
| 5 | Casting of ground and veranda slab | bar: Month 1 5
Inspection during casting of reinforced concrete floor slab | bar: Month 1 5
3.2 | Superstructure
| 1 | Construction of sub wall and installation of damp proof | bar: Month 2 6 to Month 2 7
| 2 | Construction of walling and beams | bar: Month 2 7 to Month 2 9
3.3 | Construction of roofing
| 1 | Assembly of all roof sections | bar: Month 2 8 to Month 2 9
Inspection of roof sections before installation | bar: Month 3 10
| 2 | Installation of roof sections on the building | bar: Month 3 10
| 3 | Fitting of roof sheeting and guttering | bar: Month 3 10 to Month 3 11
| 4 | Fitting of wire mesh to enclose open ends of roof | bar: Month 3 11
3.4 | Internal and external fittings and finishes
| 1 | Fitting of windows | bar: Month 3 10
| 2 | Fitting of doors | bar: Month 3 10 to Month 3 11
| 3 | Fixing of plumbing fittings including plastic roof tanks | bar: Month 3 10 to Month 3 11
Inspection of fittings, finishes and roofing | bar: Month 3 11
| 4 | Fixing water closets and urinals | bar: Month 3 11 to Month 3 12
| 5 | Construction of hand wash basins | bar: Month 3 12 to Month 3 13
| 6 | Fitting of shower heads and parapet wall | bar: Month 3 12 to Month 3 13
| 7 | Fixing of electrical fittings | bar: Month 3 12 to Month 3 13
Inspection of fittings and finishes | bar: Month 3 13
| 8 | External finishes of veranda (concrete benches, coping, arc beams) | bar: Month 3 11 to Month 3 13
| 9 | External wall finishes (keying, plastering) | bar: Month 3 13
| 10 | Internal wall and floor finishes (plastering, tiling, painting, mirrors) | bar: Month 3 13 to Month 3 14
| 11 | Internal finishes of operators room (timber counter, shelves etc.) | bar: Month 3 13 to Month 3 14
| 12 | Painting of windows and doors | bar: Month 4 15
Final inspection of fittings and finishes | bar: Month 4 15
3.5 | Toilet sewerage
| 1 | Construction of manholes including piping | bar: Month 2 9 to Month 3 10
| 2 | Installation of ventilation pipe | bar: Month 3 11
|  |  |  | Start date: | [12 empty] | End date:
|  |  | Months | Month 1 1: Month 1; Month 2 6: Month 2; Month 3 10: Month 3; Month 4 15: Month 4
No | Description |  | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
4 | On-site treatment system
| 1 | Excavation works | bar: Month 1 2 to Month 1 3
Inspection after finalization of excavation to verify proper levels | bar: Month 1 3
| 2 | Casting of strip foundation | bar: Month 1 3 to Month 1 4
| 3 | Shuttering and casting of reinforced concrete floor slab | bar: Month 1 4
Inspection during casting of reinforced concrete floor slab | bar: Month 1 5
| 4 | Masonry until piping level with concurrent external plastering | bar: Month 1 5
Training on baffle pipe setting and internal plastering | bar: Month 1 5
| 5 | Fixing of baffle pipes to accurate levels | bar: Month 2 6
| 6 | Finish masonry up to roof slab level with concurrent external plastering | bar: Month 2 6
| 7 | Internal water proof plastering of all walls | bar: Month 2 6 to Month 2 7
Inspection after finalization of plastering work | bar: Month 2 7
| 8 | Masonry of inlet chamber and trench | bar: Month 2 7
| 9 | Preparation of shuttering and reinforcement for roof slab | bar: Month 2 8
Inspection during casting of reinforced roof slab | bar: Month 2 8
| 10 | Casting of reinforced roof slab | bar: Month 2 8
| 11 | Pre-casting of all manhole lids and covers | bar: Month 1 5 to Month 2 8
Training of manhole construction and biogas piping | bar: Month 2 9
| 12 | Construction of all manholes | bar: Month 2 9 to Month 3 10
| 13 | Complete biogas piping to final destination (café etc.) | bar: Month 3 10
Inspection after finalizing of manholes and biogas piping | bar: Month 3 10
Training on manhole sealing | bar: Month 3 10
| 14 | Inoculation of all chambers with cow-dung | bar: Month 3 10 to Month 3 11
| 15 | Sealing of gas-tight manholes and inspection manholes | bar: Month 3 11
Inspection for purpose of pressure testing of DTS and biogas piping | bar: Month 3 11
| 16 | Pressure testing of treatment system and biogas piping | bar: Month 3 11
| 17 | Landscaping | bar: Month 3 11 to Month 3 12
Final inspection after finalizing of landscaping | bar: Month 3 12
5 | Drainage of effluent to sewerage or storm water network
| 1 | Excavation and laying the pipeline | bar: Month 2 8 to Month 2 9
| 2 | Backfill all the laid sections of the pipeline | bar: Month 2 9
6 | Connecting water supply to toilet facility
| 1 | Excavation and laying the pipeline | bar: Month 2 9 to Month 3 10
| 2 | Backfill all the laid sections of the pipeline | bar: Month 3 10
7 | Testing of complete system for leakages and other defects
| 1 | Test run the water pipeline system | bar: Month 3 11
8 | Other trainings
| 1 | Training for operator, WSB and WSP on operation and maintenance of toilet facility, treatment system and biogas piping | bar: Month 4 16
9 | Final inspections
| 1 | Inspection after complete finalization of all structures | bar: Month 4 15
| 2 | Remedy all the defects and leaking sections/fittings | bar: Month 4 15 to Month 4 17
| 3 | Handing over of site from contractor to WSP | bar: Month 4 17
10 | COMMISSIONING | bar: Month 4 18
|  |  |  | Start date | [12 empty] | End date:
NB:
The start date of this plan should be consistent with the end date of the procurement plan, It is important that the implementation plan or technical works be restricted to not more than five (5) months

## 2. Accom. Measures. Imp. Prog.
Appendix 4b
Project Implementation Plan: Accompanying Measures
Activity |  | Status (3) | Period:>>>> | Month 1 |  |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  |  | Month 8
CARD | Activities mainly taking place in the project area(s) | N / P / I / C | Responsibility \ Week: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
1 | Appointment of a Customer Services Assistant (CSA) |  | WSP
2 | Preliminary project Planning Meeting (WSP, WSP, Municipality) |  | WSP/Consultant
3 | Formation of the Project Task Team |  | WSP/Consultant
4 | Project Planning meeting with stakeholders |  | Task Team
| Data collection: Confirming the need for Public Sanitation Facility (PSF) (3) |  | Task Team
| Data collection: Identification of target groups & their specific sensitisation requirements |  | Task Team
6 | Internal Task Team activities / Preparation and planning of the Project Implementation Programme |  | Task Team
6 | Preparation/adaptation of the budget for the non-technical project component |  | Task Team
7 | Preparation project progress indicators and the community participation approach |  | Task Team
8 | Public meeting (baraza) to introduce the (PSF) project |  | Task Team
12 | Putting up posters and signs (community mobilisation) |  | Task Team
9 | First series of public meetings in PSF catchment areas (zones) |  | Task Team
9 | Second series of public meetings in PSF catchment areas (zones) |  | Task Team
19 | Technical works |  | Contractor/WSP/Task Team
10 | Public meeting (baraza) to explain the project (including PSF operation) |  | Task Team
10 | Implementation of the sensitisation campaign |  | Task Team
11 | Implementation of "Water & Sanitation Shows" ("Maji Barazas") |  | Task Team/Drama Group
12 | Putting up posters & signs |  | Task Team
13 | Preparation and broadcast of the radio message |  | Task Team
14 | Public announcements |  | Task Team
15 | Group discussions (formal) |  | Task Team
15 | Group discussions (informal) |  | Task Team
16 | Drama group sketches (public health and water supply & the community) |  | Task Team/Drama Group
17 | Guided tours of the WSP treatment works, office, network section, etc. |  | Task Team
18 | Special measures and SWAS |  | Task Team/Municipality
19 | Coordination of Technical Works and the Non-Technical Project Component |  | Task Team/Contractor/WSP
20 | Identification, recruitment and training of the PSF Operators & WSP staff |  | Task Team/WSP
21 | Preparing the commissioning of the PSF |  | Task Team/WSP/Police
21 | Commissioning and inauguration of the PSFs |  | Task Team/WSP/Police
21 | Inauguration of the project (PSFs) |  | Task Team/WSP/Guest
21 | Day-to-day management of the Operator(s) /On-the-job training of Operators |  | WSP/Task Team
>> | Operation of the project |  | WSP/WSP Billing Section | bar: Month 6 25 to Month 8 36
22 | (First) Evaluation of the projects (PSFs) |  | WSP/External Evaluator/WSTF | bar: Month 8 36
Activity |  | Status (3) | Period:>>>> | Month 1 1: Month 1; Month 2 6: Month 2; Month 3 10: Month 3; Month 4 15: Month 4; Month 5 19: Month 5; Month 6 24: Month 6; Month 7 28: Month 7; Month 8 33: Month 8
No. | Activities mainly taking place in the office of the WSP | N / P / I / C | Responsibility \ Week: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A | WSP management approves the (composition of the) Project Task Team |  | WSP Management
B | WSP management approves the Project Implementation Programme |  | WSP Management
C | The WSP develops the PSF Management System (document) |  | WSP, Field Monitor
D | Discussion of the proposed PSF Management System by WSP management |  | WSP/Field Monitor
E | Ongoing exchange of information between WSP management, Task team, Contractor and WSTF |  | Task Team/WSP
F | On-the-job training of the CSA |  | Task Team
G | Integration of the PSFs into the billing system |  | Billing Section / /Field Monitor
H | Adaptations of PSF Management System on basis of first experiences |  | Billing Section / /Field Monitor
I | Reporting by the WSP |  | WSP
J | Preparation of the Project Completion Report |  | WSP
1): WSP = Water Service Provider, WSB = Water Services Board, WSTF = Water Services Trust Fund
2): N = Not initiated; P being Prepared; I = being Implemented; C = Completed activity
3): This activity is only necessary if data on the project area is not sufficient

## 3. Acco. Meas. Progr. (example)
Appendix 4b
Project Implementation Plan: Accompanying measures (example)
Activity |  | Status (3) | Period:>>>> | Month 1 |  |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  |  | Month 8
CARD | Activities mainly taking place in the project area(s) | N / P / I / C | Responsibility \ Week: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
1 | Appointment of a Customer Services Assistant (CSA) |  | WSP | bar: Month 1 1 to Month 1 2
2 | Preliminary project Planning Meeting ( WSP, Municipality) |  | WSP/Consultant | bar: Month 1 3
3 | Formation of the Project Task Team |  | WSP/Consultant | bar: Month 1 4 to Month 1 5
4 | Project Planning meeting with stakeholders |  | Task Team | bar: Month 2 6
5 | Data collection and needs assessment |  | Task Team | bar: Month 2 7 to Month 2 9
5 | Data collection report and calculating the number of Public Toilets |  | Task Team | bar: Month 2 9 to Month 3 10
6 | Internal Task Team activities / Planning of the Project Implementation Programme |  | Task Team | bar: Month 2 9 to Month 3 11
6 | Preparation/adaptation of the budget for the non-technical project component |  | Task Team | bar: Month 3 11
7 | Preparation project progress indicators and the community participation approach |  | Task Team | bar: Month 2 9; Month 3 11
8 | Public meeting (baraza) to introduce the project |  | Task Team | bar: Month 3 12
12 | Putting up postersand signs (community mobilisation) |  | Task Team | bar: Month 3 12
9 | First series of public meetings in Toilet catchment areas (zones) |  | Task Team | bar: Month 3 12 to Month 3 13
9 | Second series of public meetings in Toilet catchment areas (zones) / Toilet site selection |  | Task Team | bar: Month 3 13 to Month 3 14
19 | Technical works |  | Contractor/WSP/Task Team | bar: Month 3 10 to Month 5 20; Month 5 22 to Month 5 23
10 | Public meeting (baraza) to explain the project |  | Task Team | bar: Month 4 18 to Month 5 19
10 | Implementation of the sensitisation campaign |  | Task Team | bar: Month 3 14 to Month 5 21
11 | Implementation of "Water and Sanitation Shows"(Maji Barazas) |  | Task Team/Drama Group | bar: Month 4 18 to Month 5 20
12 | Putting up posters and signs |  | Task Team | bar: Month 4 17; Month 5 20
13 | Preparation and broadcast of the radio message |  | Task Team | bar: Month 4 18; Month 5 20 to Month 5 21
14 | Public announcements |  | Task Team | bar: Month 4 17; Month 5 22
15 | Group discussions (formal) |  | Task Team | bar: Month 2 9 to Month 5 22
15 | Group discussions (informal) |  | Task Team | bar: Month 1 1 to Month 6 26
16 | Drama group sketches (public health and water supply & the community) |  | Task Team/Drama Group | bar: Month 4 18 to Month 5 20
17 | Guided tours of the WSP treatment works, office, network section, etc. |  | Task Team | bar: Month 3 11; Month 4 16; Month 5 21
18 | Special measures and SWAS |  | Task Team/Municipality | bar: Month 8 33 to Month 8 34
19 | Coordination of Technical Works and the Non-Technical Project Component |  | Task Team/Contractor/WSP | bar: Month 1 1 to Month 5 22
20 | Identification, recruitment and training of the Public Toilet Operators & WSP staff |  | Task Team/WSP | bar: Month 3 14; Month 4 17; Month 5 19 to Month 5 20
21 | Preparing the commissioning of the project (Public Toilet) |  | Task Team/WSP/Police | bar: Month 5 22 to Month 5 23
21 | Commissioning and inauguration of the (Public Toilet) |  | Task Team/WSP/Police | bar: Month 5 23
21 | Inauguration of the project (Public Toilet) |  | Task Team/WSP/Guest | bar: Month 7 30
21 | Day-to-day management of the operator (Public Toilet) |  | WSP/Task Team | bar: Month 5 23 to Month 6 24
>> | Operation of the project |  | WSP/WSP Billing Section | bar: Month 6 25 to Month 8 36
22 | (First) Evaluation of the Toilet Scheme |  | WSP/External Evaluator/WSTF | bar: Month 8 35 to Month 8 36
Activity |  | Status (3) | Period:>>>> | Month 1 1: Month 1; Month 2 6: Month 2; Month 3 10: Month 3; Month 4 15: Month 4; Month 5 19: Month 5; Month 6 24: Month 6; Month 7 28: Month 7; Month 8 33: Month 8
No. | Activities mainly taking place in the office of the WSP | N / P / I / C | Responsibility \ Week: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A | WSP management approves the (composition of the) Project Task Team |  | WSP Management | bar: Month 1 3
B | WSP management approves the Project Implementation Programme |  | WSP Management | bar: Month 3 11
C | The WSP develops the Public Toilet Management System (document) |  | WSP, Field Monitor | bar: Month 3 13 to Month 4 15
D | Discussion of the proposed Public Toilet system management by WSP management |  | WSP/Field Monitor | bar: Month 4 16
E | Ongoing exchange of information between WSP management, Task team, Contractor and WSTF |  | Task Team/WSP | bar: Month 1 1 to Month 8 36
F | On-the-job training of the CSA |  | Task Team
G | Integration of the Public Toilet system into the billing system |  | Billing Section / /Field Monitor | bar: Month 5 19; Month 5 22 to Month 6 26
H | Adaptations of Public Toilet Management System on basis of first experiences |  | Billing Section / /Field Monitor | bar: Month 7 31
I | Reporting by the WSP |  | WSP
J | Preparation of the Final Report |  | WSP | bar: Month 7 29 to Month 7 30
1): WSP = Water Service Provider, WSB = Water Services Board, WSTF = Water Services Trust Fund
2): N = Not initiated; P being Prepared; I = being Implemented; C = Completed activity
3): This activity is only necessary if data on the project area is not sufficient