## 1. Progress Report
Water Services Trust Fund | [7 empty] | Sheet 1
Monthly Progress Report of the Water Service Provider
Project name: |  |  |  | Project No.: |  | Month:
Name of WSP: |  |  |  | Town: |  | Type of project:
Name of WSB: |  |  |  | Project area: |  | Type of project area:
Commencement date: |  |  |  | Original estimated completion date: |  | Estimated completion date:
A. | Project Progress in Month
Use bullet points to summarise the main project activities and progress during the last month. Any significant matters arising that adversely affect the timing and/or successful completion of the project should be detailed in the next section. (Photographs should be attached /submitted illustrating progress of physical items, events held & other matters of interest.).
B. | Issues Arising/In Progress
Give detail of issues that potentially threaten the successful completion of the project or have a significant impact on the timing of completion. Indicate the cause of the problem, it’s likely impact and what compensating actions are proposed or have been taken. If the estimated completion date has changed in the month then there must be an entry in this section. (Attach a separate sheet if necessary.).
List of attached documents:
1
2
3
4
5
Signature of WSP staff member who prepared the report: |  |  | Date:
|  |  |  | Checked by: | Signed: |  | Date:

## 2. Progress & Milestones (1)
Water Services Trust Fund | [10 empty] | Sheet 2
Monthly Report of the Water Service Provider
Project name: |  |  |  | Project No.: |  |  |  | Month:
WSP: |  |  |  | Town: |  |  |  | Names of all FMs:
WSB: |  |  |  | Project area:
Commencement date: |  |  |  | Original estimated completion date: |  |  |  | Estimated completion date:
C | Reporting on Milestones and Specific Activities
Milestone |  | Project Phase & Scope of Services (1) |  | Status (2) | Progress (3)/Observations | Issues arising | Original target date | Revised target date | Actual date | Recommendations
|  | Preparatory Activities |  | N/P/C/A/NA | G/F/U/N/NA
1 |  | Preparation of the detailed Work Plan
Preparation of the technical works programme
>> |  | 2 | Appointment of a Customer Services Assistant (CSA)
See Note 4 |  | 3 | Preliminary Project Planning Meeting (WSP, WSP, Municipality)
|  | 4 | Final version of the work programme prepared
|  | 5 | Bidding documents in line with the FIDIC conditions of contract prepared
|  | 6 | The invitation of bids, evaluation of bids and awarding of contracts by the WSP is done transparently and in accordance with the Public Procurement and Disposal Act, 2005
|  | 7 | The Contractor's Contract prepared
|  | 8 | Project Planning meeting with stakeholders including the Contractor
|  | 9 | Contractor has prepared the Work Plan
2 |  | 10 | The most appropriate site(s) for the construction of the sanitation facility (facilities) has (have) been secured (taking legal issues, environmental concerns and local social conditions into account)
Project implementation
| >> | ENGINEERING (Community-based activities) >>
|  | 11 | Periodic inspections of works during distinct milestones to ensure compliance to the set works specifications, time and cost are undertaken
|  | 12 | The contracts signed between the WSP and Contractors are respected (contract management)
|  | 13 | Site meetings are organised & WSP staff are participating effectively in these meetings to see all bottlenecks impeding implementation of works are overcome
|  | 14 | Technical works and all materials used are of good quality
|  | 15 | Technical works are coordinated with the accompanying measures (to be ensured together with Task Team & Contractor)
|  | 16 | Poor quality of works, deviations from technical drawings and delays are reported to the WSB & WSTF
| >> | SOCIAL (Community-based activities) >>
|  | 17 | Identification, recruitment and training of the Facility Operators & relevant WSP staff
|  | 11 | Public meeting (baraza) to introduce the project
|  | 12 | Putting up posters (community mobilisation)
|  | 13 | First series of public meetings in the sanitation facility catchment area(s)
|  | 14 | Second series of public meetings in the sanitation facility catchment area(s)
|  | 15 | Technical works
|  | 16 | Public meeting (baraza) to explain the project (the operation of the sanitation facility)
|  | 17 | Implementation of the sensitisation campaign
|  | 19 | Putting up posters
|  | 20 | Preparation and broadcast of the radio message
|  | 21 | Public announcements
|  | 22 | Group discussions (formal)
|  | 23 | Group discussions (informal)
|  | 24 | Drama group sketches (sanitation & public health)
|  | 25 | Guided tours of the WSP treatment works, sewage treatment plant, office, network section, etc.
|  | 26 | Special measures and SWAS
|  | 27 | Coordination of Technical Works and the Non-Technical Project Component
| >> | FINANCIAL >>
|  | 10 | All improvements/systems developed (see Preparatory Activities) are being implemented
|  | 11 | Preparation of the public sanitation facility management concept
|  | 12 | The public sanitation facility (-ies) is (are) integrated in the billing system
|  | 13 | Start of technical works
|  | 14 | The WSP ensures that it receives value for money (for works) before payments are made
|  | 15 | The capacity & performance of the WSP staff responsible for water supply & sanitation in low income areas is strenthened
|  | 16 | The WSP is establishing a strong presence in the project areas and other low income urban areas
|  | 17 | The WSP is developing and implementating a (pro-poor) customer care concept
|  | 18 | The FM periodically briefs the Managing Director on the progress and the challenges facing the implementation of works
|  | 19 | The operational phase of the project is being prepared
|  | 20 | Coordination of Technical Works and the Non-Technical Project Component
Training of Facility Operator(s) >>
3 |  | 28 | Identification, recruitment and training of the Public Sanitation Facility Operator(s) & WSP staff
Notes: |  | 1): | The Task Team may decide not to implement all activities mentioned in this sheet. Progress, indicators and outputs should essentially be based upon the programme developed by the Task Team
|  | 2): | N = Not yet started; I = Initiated; P = In progress; C = Completed; A = Activity not included or planned for; NA = Non-applicable
|  | 3): | G = Good progress; F = Progress is fair; U = Progress is unsatisfactory; N = No progress; NA = Non-applicable
|  | 4): | The numbering is compatible with the Field Monitors Monthly Progress Report

## 2. Progress & Milestones (2)
Water Services Trust Fund | [10 empty] | Sheet 3
Monthly Report of the Water Service Provider
Project name: |  |  |  | Project No.: |  |  |  | Month:
WSP: |  |  |  | Town: |  |  |  | Names of all FMs:
WSB: |  |  |  | Project area:
Commencement date: |  |  |  | Original estimated completion date: |  |  |  | Estimated completion date:
C | Reporting on Milestones and Specific Activities
Milestone |  | Project Phase & Scope of Services (1) |  | Status (2) | Progress (3)/Observations | Issues arising | Original target date | Revised target date | Actual date | Recommendations
|  | Project commissioning and operation of the scheme |  | N/P/C/A/NA | G/F/U/N/NA
ENGINEERING (Commissioning of the project) >>
>> |  | 18 | The commissioning of the project public sanitation facility(ies)) is prepared
See Note 4 |  | 19 | The WSPs has carried out the detailed inspection of the completed technical works (attention is given to detail!)
|  | 20 | The project has been commissioned (the entire project or stages)
Operation of the project scheme >>
|  | 21 | The entire project scheme, as well as each individual facility, functions according to expectations
|  | 22 | Sufficient quantities of treated water reach the project facility (-ies)
|  | 23 | Water pressure & water quality are adequate, there is sufficient flow in the sewer, septic tank or biodigester is functioning
|  | 24 | Initial wear and tear has been assessed and solutions have been implemented
|  | 25 | The Contractor respects the Defects Liability Period (DLP)
|  | 26 | The project has been inaugurated
|  | 27 | WSP staff is carrying out all necessary maintenance & repair work
|  | 28 | The WSP is disconnecting / regularising & meter all illegal connections
SOCIAL (Commissioning of the project) >>
|  | 29 | Preparing the commissioning of the project (public sanitation facility(-ies))
|  | 30 | Commissioning of the public sanitation facility(-ies)
|  | 31 | Inauguration of the project
Operation of the project scheme >>
|  | 32 | Day-to-day management of the facility Operator(s) and the project infrastructure/Training of Operators on-the-job
|  | 33 | The WSP is carrying out regular (hygiene) inspections
|  | 34 | Operators deliver a good service to their customers and maintain their facility
FINANCIAL (Commissioning of the project) >>
|  | 22 | The Billing Section/Dept. participates in the preparation of the commissioning of the project
Operation of the project scheme >>
|  | 23 | Day-to-day management of the Operators and the facility/Training of Operators on-the-job
|  | 24 | The WSP monitors the financial performance of the project scheme (collection efficiency, revenue)
|  | 26 | Implementation of the customer care concept
4 |  | 27 | The WSP has established a strong and lasting presence in the project area(s)
Activities taking place throughout the project
|  | 29 | On-the-job training of the CSA
|  | 30 | On-the-job training of other WSP staff
|  | 31 | Field Monitors periodically brief the Managing Director on progress and challenges facing the implementation of works
|  | 32 | Field Monitors provide technical and organisational advice to the WSP, the Task Team and the Contractor
|  | 33 | There is good coordination of works and activities within the Task Team and with the WSP
|  | 34 | All irregularities are reported (acts of corruption, theft, misuse, etc.)
|  | 35 | Field Monitors advice the WSTF on necessary actions/interventions (support measures and sanctions)
Notes: |  | 1): | The Task Team may decide not to implement all activities mentioned in this sheet. Progress, indicators and outputs should essentially be based upon the programme developed by the Task Team
|  | 2): | N = Not yet started; I = Initiated; P = In progress; C = Completed; A = Activity not included or planned for; NA = Non-applicable
|  | 3): | G = Good progress; F = Progress is fair; U = Progress is unsatisfactory; N = No progress; NA = Non-applicable
|  | 4): | The numbering is compatible with the Field Monitors Monthly Progress Report

## 3a. Progress Tech. Works
Yes
No
Monthly Progress Report of the Water Service Provider |  |  | (Month-Year) | 2010-01-01
Project Area/Name: |  |  | >>
Project Number: |  |  | >>
Name of Field Monitor: |  |  | >>
1. GENERAL PROGRESS/INFORMATION |  |  |  |  | Sheet 4a
No. | ITEM | YES/NO | if "NO" PLEASE COMMENT
1 | Are Approved Drawings available on Site (Latest Version)?
2 | Is a site instruction book on site and up-to-date?
3 | Are Approved Materials used (reinforcements, cement, aggregates, fittings, finishes)?
4 | Are Specified concrete cube test being achieved?
5 | Is Concrete Surface neat, smooth, even, uniform and free from honeycombing, ridges and cracks?
6 | Are Cast in items in accordance with drawing (incl. sleeves)?
7 | Are floor finishes complete, floors clean, skirtings complete, trench covers complete?
8 | Are all wall joineries complete as per the drawing?
9 | Are all doors complete and operate correctly, check keys/locking mechanism are available for handover?
10 | Are all windows complete and operates / fixed correctly.
11 | Is all shelving and other fittings fixed to specification?
12 | Are the Pipes, fittings, plumbing & drainage Materials to specification?
13 | Is the vault roofing/roof properly fixed and watertight?
14 | Are there leakages in the plumbing works, wc, wash hands basins, cisterns, roof space tanks?
15 | Has the As Built check been done, location, dimensions elevations, walls, windows, doors, roof, to conform with the drawings?
16 | Is the layout of the site as per latest drawing, check surrounding area is clean and free of debris area graded to final level?
17 | Is the painting and decorations complete to latest finishes schedule?
1. GENERAL PROGRESS/INFORMATION (cont.) |  |  |  |  | Sheet 4b
No. | ITEM | YES/NO | if "NO" PLEASE COMMENT
19 | Is the Site Drainage in accordance with the drawings?
20 | Are the trenches complete and covers installed?
21 | Are the pedestrian access ways complete and unobstructed?
22 | Has the Facility been branded/signposted as specified?
23 | Has the Contractor approved the avaiable Work Programme and updated it?
24 | Is Construction in accordance with the approved work programme?
25 | Has the Contractor submitted any invoices?
26 | Are the invoices in line with the progress in construction and budget lines?
27 | Are the works within budget with no cost overruns?
28 | Are the contractors payments up to date and as scheduled?
29 | Is Q.A. documentation available for inspection if required? | 3 | Roof Slab
30
31
2. PROGRESS OF WORKS |  | % COMPLETE | % PLANNED |  | Sheet 4c
1 | Substructure
2 | Floor slab
3 | Superstructure
4 | Roofing
5 | Fittings (Sanitary)
6 | Doors and Windows
7 | Finishes
8 | Overall | #VALUE! | #VALUE!
3. CONTRACTORS INVOICES |  | KSh | DATE | % of TOTAL
1 | Total approved project value
2.1 | 1st Invoice received from Contractor |  |  | #DIV/0!
2.2 | 2nd Invoice received from Contractor |  |  | #DIV/0!
2.3 | 3rd Invoice received from Contractor |  |  | #DIV/0!
3 | Total Invoices |  |  | #DIV/0!
4 | Total funds received from WSTF |  |  | #DIV/0!
4. RECOMMENDATIONS |  |  |  |  | Sheet 4d
1
2
3
4
5
6
7
8
9
10

## 3b. Checkout Guidance Notes
Monthly Progress Report of the Water Service Provider
CHECKOUT AND GUIDANCE NOTES
1. STRUCTURAL CONCRETE
ITEM | DESCRIPTION/SCOPE OF CHECKOUT
1 | Check out that Approved drawings (latest revision) are on site and are being used
2 | Check out the dimensions, location and elevation of the concrete structure is in accordance with approved drawings (latest revision)
3 | Checkout that approved materials are being used (reinforcements, cement, aggregates)
4 | Check out the specified concrete cube test records are complete and up to date
5 | Checkout steel float finish where specified xxxxxxxxxxxxx
6 | Checkout that the concrete surface neat, smooth, even, uniform and free from honeycombing, ridges and cracks
7 | Check out that all joineries are in accordance with drawing
8 | Check out forming and sealing of Joints as specified
9 | Check out watertight structures conform to specifications
10 | Checkout grouting to specification with 45 degree finish
11 | Check out cast in items in accordance with drawing (including sleeves)
12 | Checkout Compaction as specified.
2. PUBLIC SANITATION FACILITY STRUCTURE (INTERNAL)
ITEM | DESCRIPTION/SCOPE OF CHECKOUT
1 | Note structure reference and checkout that the layout conforms to latest drawing
2 | Check floor finishes complete, floors clean, skirting complete, trench covers complete.
3 | Check all wall finishes complete as per finishes schedule
4 | Check out all doors are complete and operate correctly check keys are available for handover
5 | Check all windows are complete and operates / fixed correctly check cracked or damaged panes
6 | Check all cupboards units and fittings etc have been installed and all installation complete
7 | Check plumbing ,sanitary wears, roof tanks, taps, etc. are complete operational and not leaking
8 | Check all ceilings are complete to finishes specification
9 | Check lighting installation complete and operational (where applicable) and test certificates available and illumination levels checked
10 | Check painting and decorations complete to latest finishes schedule
11 | Check Q.A. documentation is available for inspection if required.
3. PUBLIC SANITATION FACILITY STRUCTURE (EXTERNAL)
ITEM | DESCRIPTION/SCOPE OF CHECKOUT
1 | Checkout layout of drawing as per latest drawing, check surrounding area is clean and free of debris area graded to final level
2 | Check pedestrian access ways and the veranda are complete and unobstructed
3 | Check drainage trenches are complete and covers installed
5 | Check all doors are complete and operate correctly check keys are available for handover
6 | Checkout windows are complete and operate / fixed correctly check no window panes are cracked or broken
7 | Check roofing is complete and watertight
8 | Check hips and valleys sealed, flashings complete rainwater goods installed bird proofing complete Eaves closures complete
9 | Check all paintings are complete to finishing specification
10 | Check CuAD drainage is complete tested all manhole covers installed
11 | Check installation complete and operational

## 3. Progress Acc. Measures
Water Services Trust Fund
Monthly Progress Report of the Water Service Provider | [6 empty] | Sheet 5
Project name: |  | Project No.: |  |  | Month:
WSP: |  | Town: |  |  | Names of FMs:
WSB: |  | Project area:
Commencement date: |  | Original estimated completion date: |  |  | Estimated completion date:
Activities Undertaken |  | No. | Description | Main sub-activities |  | Remarks
A | Preparatory activities (office-based activities)
1 | Preparation of the detailed Work Plan (FM's)
2 | Appointment of CSA (or similar position)
3 | Establishment of Project Task Team
4 | Project planning meeting (with stakeholders)
5 | Collection of data/assessment of needs
6 | Preparation of the accompanying measures programme
7 | Preparation of progress indicators
8 | Adaptation of the detailed Work Plan
9
B | Meetings with stakeholders
10 | Meetings with Council
11 | Site identification meetings
12 | Task Team Meetings
13 | Meetings with the other FMs
14 | Meetings with WSP management
15 | Meetings with the WSB
16 | Project coordination meetings
17
C | Community mobilisation and sensitisation
18 | Training (on-the-job) of WSP staff
19 | Identification of yard tap beneficiaries
20 | Barazas
21 | Group discussions
22 | Drama group performances
23 | "Water & Sanitation Shows" ("Maji Barazas")
24 | Public announcements
25 | Preparation of posters
26 | Putting up posters
27 | Preparation of radio broadcasts
28 | Radio broadcasts
29 | Identification of Public Sanitation Facility Operator(s)
30 | Training of Public Sanitation Facility Operator(s)
31 | Guided tours of the treatment works, office, etc.
32
D | Project commissioning activities
33 | Preparing project commissioning
34 | Project commissioning
35
E | Project operation activities
36 | Training (on-the-job) of Facility Operator(s)
37 | Public Sanitation Facility inspections
38 | Training (on-the-job) of WSP staff
39 | Sensitisation of residents
40

## 4. Summary Financial Report
Monthly Progress Report of the Water Service provider |  |  |  |  | WSP Summary Financial Report |  |  |  | Sheet 6
Project name: |  |  |  | Project No.: |  |  | Month:
WSP: |  |  |  | Town: |  |  | Names of FMs:
WSB: |  |  |  | Project area:
Commencement date: |  |  |  | Original estimated completion date: |  |  | Estimated completion date:
|  |  | Actual |  | Actual | Cumulated Expenditure |  | Budget | Projected Variance
|  | From: | 2008-01-01 |  | 2008-03-01
|  | To: | 2008-02-29 |  | 2008-03-31
Funding
| WSTF Funding |  | 0 |  | 0 | 0 |  | 0 | 0
| Other Funding |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0
Expenditure
| Construction Works |  | 0 |  | 0 | 0 |  | 0 | 0
| Supervision Works |  | 0 |  | 0 | 0 |  | 0 | 0
| Sanitation and Hygiene |  | 0 |  | 0 | 0 |  | 0 | 0
| Community Mobilisation and Support |  | 0 |  | 0 | 0 |  | 0 | 0
| Utility Defined |  | 0 |  | 0 | 0 |  | 0 | 0
| Utility Defined |  | 0 |  | 0 | 0 |  | 0 | 0
| Overheads |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0
Balance of Funding in Period
| Funding on Hand at Start of Period |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0
Balances
Bank Balance
| Cash on Hand |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0 |  | 0 | 0
Notes on the Monthly Financial Report:
1 | The Format of the report is as per the accounting tool with the addition of the columns for comparison with budget and revised forecasts
2 | The aim of the report is to prompt all involved to identify variances from budget at an early stage
3 | The discipline and skill to reforecast promptly and with reasonable accuracy will take some time to develop, but it is better to start immediately so that the learning
is as early as possible, but some tolerance will be required from the WSTF
4 | The rows indicating 'utility defined' are an indicator that the report should be adopted in its content depending on the project budget
5 | The report does not change any obligation to account for the moneys advanced as defined elsewhere or in the project contract

## 5. Notes on Completion
Water Services Trust Fund
WSP Monthly Progress Report
Notes on Completion
1 | The WSP must complete a report for each month.
2 | Reports are to be submitted to WSTF to be received no later than the 10th day of the following month.
3 | Reports are to be copied to the Water Services Board.
4 | The purpose of the reports is to relay information to WSTF so that it can judge the progress of projects. It will be assumed that unless deviations from plan are reported work is progressing according to the original plan, therefore WSPs have an obligation to report all significant matters that are a deviation from plan or might cause a deviation from plan.
5 | The WSP should report on:
o The quality of the works (technical works and the accompanying measures).
o Progress made.
o Work Plan.
o Challenges faced.
o Delays and the causes of these delays.
o Performance of the Project Task Team.
o The involvement/participation of the other stakeholders (WSP, WSB, Chief, residents, PHO, CHEW, etc.).
o Is the project demand-driven?
o Quality of the data used.
o Functioning of the FM Team.
o Financial management of the project.
o Vandalism and theft.
o Irregularities observed (corruption).
6 | It is important that the WSTF understands the problems encountered and what is being done about them. In this respect, when an issue needs some detailed explanations to be submitted, enter the issue on the form and state ‘see attached’.
7 | Keep narrative to a minimum by using bullet points. It is the information that is important, not the quality of the written word.
8 | The WSP may attach photographs to this report showing physical progress or community-based activities (accompanying measures).